## Slide 1: Information meeting for CEC, INES, GEOLOGY
2023-06-07

## Slide 2: Today’s meeting agenda about the co-location and co-organisation of CEC, INES and Geology
Background
  2021– 2022
  2023 – until today
Project organisation and project plan – for the rest of 2023
Plans for the following steps – for the rest of 2023
2024
The basic premises review – Hanieh Heidarabadi
Questions
Mingle with snacks and refreshments - Welcome

## Slide 3: Background 2021-2022
Future Science seminars - arranged by the Faculty of Science
Future research landscape
Costs
Scientific and educational values
The heads of CEC, INES and the Department of Geology - feasibility study on the conditions for co-location and co-organisation
One internal and one external investigation was carried out
Meetings and presentations at departments
Decision to carry out a basic premises review

## Slide 4: Background 2023 - until today
January Information to the unions (MBL)
February Orientation decision (”inriktningsbeslut”) by the Faculty Board
March and April Discussions on how to organise the countinous work
April The basic premises review was completed
May MBL
Decisions on: project plan 2023, steering committe members, project group members

## Slide 5: The project plan for 2023(decided May 2023)
  Delivery targets/objectives 2023
The re-location of Computational Biology and Biological Physics (CBBP) from Fysicum to Geocentrum II.
Test of scheduling to clarify the needs for undergraduate facilities prior to co-location.
Premises program for co-location (lokalprogram).
Identify specific issues for the continuation of the project in 2024.
Risk and impact assessment of the co-location and merger including proposed measures.
Report to the Board on activities and results achieved (meetings in June, September and November).
Deliver a report to the Board on the achievement of the 2023 project objectives (meeting December).

## Slide 6
Steering committee
Faculty Board
Project group
Faculty Office support
Dean
c
Project Organisation
LU Estates
Dialogues Representatives
Library
Lab
IT
Administra-tion
Basic education
Postgraduate education
Research
Centers

## Slide 7
The project group:
Karin Hall, Project Manager
Yann Clough, CEC
Martin Berggren, INES
Raimund Muscheler, Geology
Carina Jarl, project coordinator
Hanieh Heidarabadi, process manager
Johanne Elde, communications
Student representative GU
Student representative FU
The steering committee:
Chair: Director of CEC
Head of Geology
Head of INES
Head of Science Faculty Office
Student representative GU
Student representative FU
Project group and steering group 2023

## Slide 8: Plans for the following steps in 2023
June - Risk and impact assessment – first draft
- Plan for the interviews and dialogues with groups (”boxes” in the organizational chart)
August - Re-location of parts of CEC to Geocentrum II
September - Continue the work with the Risk and impact assessment – including proposed measures
- Start interviews and dialogues with groups – focus on possibilities and challenges
- Workshop to create a first draft of a premises program for co-location
October – December - Continue the work
- Identify concrete issues for the follow-up work in 2024
- Additional joint information meeting/workshop
- Present the 2023 achievements to the Faculty Board

## Slide 9: 2024
A new project plan (based on the 2023 achievements) will be formulated.
The Faculty Board decision (1 February 2023) stats:
“…the work must be planned so that the faculty management
can present a proposal for a decision on the establishment of
a merged department, or a final position against such a merger,
before the end of 2024.”

## Slide 10: To sum up
December 2023 – a first report to the Faculty Board – including:
a premises program,
a plan for the follow-up work in 2024.
Before the end of 2024 – a final report to the Faculty Board – including:
a proposal for a decision on the establishment of a merged department,
or a final position against such a merger.

## Slide 11: More information
Continuous updates on the faculty internal web page:
www.science.lu.se/internal
Click: Work on the coordination of a joint department

## Slide 12: End slide, logotype only

## Slide 13: Project group contacts
Karin.Hall@science.lu.se deputy dean, project manager
Carina.Jarl@science.lu.se project coordinator
Hanieh.Heidarabadi@science.lu.se process manager
Yann.Clough@cec.lu.se representative
Raimund.Muscheler@geol.lu.se representative
Martin.Berggren@nateko.lu.se representative